## Steps-FY22
Compliance and | Step | Description | Responsibility | Electronic
Followup Reviews | Step 1 | Mail Engagement Letters | Manager | Mailed
| Step 2 | Receive Phase 1 Docs (Questionnaire) | Auditor III
| Step 3 | Request Phase 2 Docs (Student Sample) | Auditor III
| Step 4 | Receive Phase 2 Docs (Student Sample) | Auditor III
| Step 5 | Analyze Docs and Complete Workpaper Review | Auditor III
| Step 6 | Complete Prelim Report and Route for Review | Auditor III
| Step 7 | First Review Complete and Route for Second Review | Auditor IV
| Step 8 | Second Review Complete and Route for Mailing | Manager
| Step 9 | Mail Prelim Report | Auditor IV
| Step 10 | Receive Response/CAP | Auditor III
| Step 11 | Analyze Response/CAP and Update Workpapers as Needed | Auditor III
| Step 12 | Complete Final Report and Route for Review | Auditor III
| Step 13 | First Review Complete and Route for Second Review | Auditor IV
| Step 14 | Second Review Complete and Route for Mailing | Manager
| Step 15 | Mail Final Report | Auditor IV
| Step 16 | Scan Documents into Alfresco and File Audit Folder | Auditor IV
Desk Audits | Step | Description | Responsibility
| Step 1 | Mail Engagement Letters | Manager
| Step 2 | Receive Documentation from LEA | Auditor III
| Step 3a | Analyze Docs and Complete Dual Attendance Query | Auditor III
| Step 3b | Analyze Docs and Complete Kinder Under 5 Query | Auditor III
| Step 3c | Analyze Docs and Complete EE No Sped Query | Auditor III
| Step 3d | Analyze Docs and Complete EE Speech Only Query | Auditor III
| Step 3e | Analyze Docs and Complete Bilingual/ESL Query | Auditor III
| Step 3f | Analyze Docs and Complete Prekindergarten Query | Auditor III
| Step 3g | Analyze Docs and Complete PRS Query | Auditor III
| Step 4 | Complete Prelim Report and Route for Review | Auditor III
| Step 5a | Return to Auditor for Corrections | Auditor IV
| Step 5b | Corrections Made, Re-Route for First Review | Auditor III
| Step 5c | First Review Complete and Route for Second Review | Auditor IV
| Step 6 | Second Review Complete and Route for Mailing | Manager
| Step 7 | Mail Prelim Report | Auditor IV
| Step 8 | Receive Response/CAP | Auditor III
| Step 9 | Analyze Response/CAP and Apply Revisions as Needed/Add CAP to Folder | Auditor III
| Step 10 | Complete Final Report and Route for Review | Auditor III
| Step 11 | First Review Complete and Route for Second Review | Auditor IV
| Step 12 | Second Review Complete and Route for Mailing | Manager
| Step 13 | Mail Final Report | Auditor IV
| Step 14 | Scan Documents into Alfresco | Auditor IV
| Step 15 | Submit Audit Adjustments to State Funding | Auditor IV
| Step 16 | Receive Actual Audit Adjustments from State Funding | Auditor IV
| Step 17 | Finalize and Close Electronic Working File and Move to Electronic File Cabinet | Auditor IV

## F22
Review Number | LEA Name | CDN | Step 1 | Step 15
F22-001 | Alief Independent School District | 101-903 | 2022-01-07 | 2022-10-14
F22-002 | Houston Independent School District | 101-912 | 2022-01-07 | 2022-09-16
F22-003 | Edgewood Independent School District | 015-905 | 2022-01-07 | 2022-10-14
F22-004 | Cypress-Fairbanks Independent School District | 101-907 | 2022-01-07 | 2022-08-12
F22-005 | Weatherford Independent School District | 184-903 | 2022-01-07 | 2022-08-26
F22-006 | Spring Independent School District | 101-919 | 2022-01-07 | 2022-10-07
F22-007 | Pasadena Independent School District | 101-917 | 2022-01-07 | 2022-09-16
F22-008 | Frisco Independent School District | 043-905 | 2022-01-07 | 2022-10-14
F22-009 | Ysleta Independent School District | 071-905 | 2022-01-07 | 2022-10-14
F22-010 | Carrollton-Farmers Branch Independent School District | 057-903 | 2022-01-07 | 2022-10-07
F22-011 | Comal Independent School District | 046-902 | 2022-01-07 | 2022-07-29

## CR22
Review Number | LEA Name | CDN | Step 1 | Step 15
CR22-001 | Beckville Independent School District | 183-901 | 2022-01-07 | 2022-11-18
CR22-002 | Big Springs Charter School | 193-801 | 2022-01-07 | 2022-10-14
CR22-003 | Bluff Dale Independent School District | 072-904 | 2022-01-07 | 2022-10-14
CR22-004 | Callisburg Independent School District | 049-905 | 2022-01-07 | 2022-09-16
CR22-005 | Celeste Independent School District | 116-902 | 2022-01-07 | 2022-10-14
CR22-006 | Houston Classical Charter School | 101-878 | 2022-01-07 | 2022-09-16
CR22-007 | San Antonio Preparatory Schools | 015-840 | 2022-01-07 | 2022-10-14
CR22-008 | The Gathering Place | 015-841 | 2022-01-07 | 2022-09-16
CR22-009 | Nova Academy | 057-809 | 2022-01-07 | 2022-09-02
CR22-010 | Premier High Schools | 072-801 | 2022-01-07 | 2023-02-10
CR22-011 | Ranger Independent School District | 067-907 | 2022-01-07 | 2022-12-30
CR22-012 | Lubbock-Cooper Independent School District | 152-906 | 2022-01-07 | 2022-10-14
CR22-013 | Blanket Independent School District | 025-904 | 2022-01-07 | 2022-10-14
CR22-014 | Levelland Independent School District | 110-902 | 2022-01-07 | 2022-11-18
CR22-015 | Fort Stockton Independent School District | 186-902 | 2022-01-07 | 2022-11-18
CR22-016 | Randolph Field Independent School District | 015-906 | 2022-01-07 | 2022-05-20
CR22-017 | Littlefield Independent School District | 140-904 | 2022-01-07 | 2022-09-16
CR22-018 | Chapel Hill Academy | 220-815 | 2022-01-07 | 2022-10-28
CR22-019 | Crockett County Consolidated Common School District | 053-001 | 2022-01-07 | 2022-09-16
CR22-020 | Douglass Independent School District | 174-911 | 2022-01-07 | 2022-09-16
CR22-021 | Eastland Independent School District | 067-903 | 2022-01-07 | 2022-10-14
CR22-022 | Edgewood Independent School District | 234-903 | 2022-01-07 | 2022-11-18
CR22-023 | Hamlin Collegiate Independent School District | 127-903 | 2022-01-07 | 2022-11-18
CR22-024 | Horizon Montessori Public Schools | 108-802 | 2022-01-07 | 2022-09-16
CR22-025 | Lasara Independent School District | 245-901 | 2022-01-07 | 2023-02-10
CR22-026 | Lovelady Independent School District | 113-903 | 2022-01-07 | 2022-09-02
CR22-027 | Lueders-Avoca Independent School District | 127-905 | 2022-01-07 | 2022-10-14
CR22-028 | Overton Independent School District | 201-908 | 2022-01-07 | 2023-03-10
CR22-029 | Palmer Independent School District | 070-910 | 2022-01-07 | 2022-10-28
CR22-030 | Perrin-Whitt Consolidated Independent School District | 119-903 | 2022-01-07 | 2022-10-14
CR22-031 | Rochelle Independent School District | 160-904 | 2022-01-07 | 2022-09-16
CR22-032 | Roscoe Collegiate Independent School District | 177-901 | 2022-01-07 | 2022-11-18
CR22-033 | San Perlita Independent School District | 245-904 | 2022-01-07 | 2023-01-06
CR22-034 | Sivells Bend Independent School District | 049-909 | 2022-01-07 | 2022-10-14
CR22-035 | Sonora Independent School District | 218-901 | 2022-01-07 | 2023-02-10
CR22-036 | STEP Charter School | 101-859 | 2022-01-07 | 2022-11-18
CR22-037 | Trinidad Independent School District | 107-907 | 2022-01-07 | 2022-10-21
CR22-038 | Waskom Independent School District | 102-903 | 2022-01-07 | 2022-09-16
CR22-039 | Water Valley Independent School District | 226-905 | 2022-01-07 | 2022-11-18
CR22-040 | Leakey Independent School District | 193-902 | 2022-01-07 | 2022-10-07
CR22-041 | Poolville Independent School District | 184-901 | 2022-01-07 | 2022-10-21
CR22-042 | Karnack Independent School District | 102-901 | 2022-01-07 | 2022-08-19
CR22-043 | Etoile Independent School District | 174-910 | 2022-01-07
CR22-044 | Whitewright Independent School District | 091-910 | 2022-01-07 | 2023-02-10
CR22-045 | Knox City-O'Brien Consolidated Independent School District | 138-902 | 2022-01-07 | 2022-10-14
CR22-046 | Friona Independent School District | 185-903 | 2022-01-07 | 2022-10-14
CR22-047 | Clarendon Independent School District | 065-901 | 2022-01-07 | 2022-10-07
CR22-048 | George West Independent School District | 149-901 | 2022-01-07 | 2022-11-18
CR22-049 | Grapeland Independent School District | 113-902 | 2022-01-07 | 2022-10-14
CR22-050 | Trinity Charter School | 046-802 | 2022-01-14 | 2022-05-13

## DA22
Review Number | LEA Name | CDN | Step 1 | Step 13 | Adjustment Amount
DA22-001 | Dallas Independent School District | 057-905 | 2022-04-01 | 2023-03-31 | -40736
DA22-002 | Fort Worth Independent School District | 220-905 | 2022-04-01 | 2023-07-21 | -15221
DA22-003 | Northside Independent School District | 015-915 | 2022-04-01 | 2023-05-19 | -185020
DA22-004 | El Paso Independent School District | 071-902 | 2022-04-01 | 2023-04-21 | -49463
DA22-005 | Aldine Independent School District | 101-902 | 2022-04-01 | 2023-03-10 | -9158
DA22-006 | Round Rock Independent School District | 246-909 | 2022-04-01 | 2023-11-10 | -22341
DA22-007 | Austin Achieve Public Schools | 227-825 | 2022-04-01 | 2023-11-10 | -2377
DA22-008 | Socorro Independent School District | 071-909 | 2022-04-01 | 2023-04-21 | -5318
DA22-009 | Mesquite Independent School District | 057-914 | 2022-04-01 | 2023-09-15 | -155116
DA22-010 | United Independent School District | 240-903 | 2022-04-01 | 2023-05-12 | -214
DA22-011 | Ector County Independent School District | 068-901 | 2022-04-01 | 2023-06-16 | 5775
DA22-012 | Austin Independent School District | 227-901 | 2022-04-01 | 2023-07-21 | -30953
DA22-013 | Texans Can Academies | 057-804 | 2022-04-01 | 2023-04-21 | -30312
DA22-014 | San Antonio Independent School District | 015-907 | 2022-04-01 | 2023-06-02 | -12375
DA22-015 | Richard Milburn Alternative High School (Killeen) | 014-801 | 2022-04-01 | 2023-09-15 | -20771
DA22-016 | Brownsville Independent School District | 031-901 | 2022-04-01 | 2023-05-12 | -23599
DA22-017 | La Joya Independent School District | 108-912 | 2022-04-01 | 2023-08-11 | -15869
DA22-018 | Garland Independent School District | 057-909 | 2022-04-01 | 2023-10-06 | -25988
DA22-019 | North East Independent School District | 015-910 | 2022-04-01 | 2023-07-21 | -11481
DA22-020 | Edinburg Consolidated Independent School District | 108-904 | 2022-04-01 | 2023-09-15 | -9168
DA22-021 | Lubbock Independent School District | 152-901 | 2022-04-01 | 2023-05-19 | -1812
DA22-022 | Keller Independent School District | 220-907 | 2022-04-01 | 2023-08-11 | -232013
DA22-023 | Clear Creek Independent School District | 084-910 | 2022-04-01 | 2024-03-15 | -80361
DA22-024 | Plano Independent School District | 043-910 | 2022-04-01 | 2023-06-16 | -9435
DA22-025 | Irving Independent School District | 057-912 | 2022-04-01 | 2023-07-21 | -7254
DA22-026 | Lewisville Independent School District | 061-902 | 2022-04-01 | 2023-05-12 | -1755
DA22-027 | Richardson Independent School District | 057-916 | 2022-04-01 | 2023-10-13 | -1853
DA22-028 | Amarillo Independent School District | 188-901 | 2022-04-01 | 2023-08-11 | -16009
DA22-029 | Conroe Independent School District | 170-902 | 2022-04-01 | 2023-05-19 | -4775
DA22-030 | Bryan Independent School District | 021-902 | 2022-04-01 | 2023-03-10 | -343
DA22-031 | Uplift Education | 057-803 | 2022-04-01 | 2023-04-07 | -12484
DA22-032 | Mission Consolidated Independent School District | 108-908 | 2022-04-01 | 2023-04-07 | -1631
DA22-033 | Judson Independent School District | 015-916 | 2022-04-01 | 2023-11-10 | -15638
DA22-034 | Birdville Independent School District | 220-902 | 2022-04-01 | 2023-06-16 | -31220
DA22-035 | Harlingen Consolidated Independent School District | 031-903 | 2022-04-01 | 2023-02-10 | -601
DA22-036 | San Angelo Independent School District | 226-903 | 2022-04-01 | 2023-06-02 | -3612
DA22-037 | Victoria Independent School District | 235-902 | 2022-04-01 | 2023-07-21 | -6370
DA22-038 | Leander Independent School District | 246-913 | 2022-04-01 | 2023-03-17 | -4930
DA22-039 | Alvin Independent School District | 020-901 | 2022-04-01 | 2023-03-10 | -16057
DA22-040 | Triumph Public High Schools-Lubbock | 152-803 | 2022-04-01 | 2023-04-21 | -4551
DA22-041 | Nacogdoches Independent School District | 174-904 | 2022-04-01 | 2023-02-17 | -2774
DA22-042 | Wylie Independent School District | 043-914 | 2022-04-01 | 2023-04-07 | -1249
DA22-043 | Three Rivers Independent School District | 149-902 | 2022-04-01 | 2023-11-17 | -53141
DA22-044 | Huntsville Independent School District | 236-902 | 2022-04-01 | 2023-02-17 | -2914
DA22-045 | San Diego Independent School District | 066-902 | 2022-04-01 | 2023-04-07 | -8905
DA22-046 | Buffalo Independent School District | 145-901 | 2022-04-01 | 2023-04-21 | 0
DA22-047 | Vidor Independent School District | 181-907 | 2022-04-01 | 2023-02-10 | -10876
DA22-048 | Trinity Basin Preparatory | 057-813 | 2022-04-01 | 2023-02-17 | -7666
DA22-049 | Palestine Independent School District | 001-907 | 2022-04-01 | 2023-02-10 | -1697
DA22-050 | Robert Lee Independent School District | 041-902 | 2022-04-01 | 2022-12-09 | 0
DA22-051 | Quinlan Independent School District | 116-908 | 2022-04-01 | 2023-03-10 | -172
DA22-052 | Lumin Education | 057-805 | 2022-04-01 | 2022-06-10 | 0
DA22-053 | Grandview Independent School District | 126-904 | 2022-04-01 | 2023-05-12 | -13530
DA22-054 | Jubilee Academies | 015-822 | 2022-04-01 | 2023-09-15 | -15831
DA22-055 | International Leadership of Texas | 057-848 | 2022-04-01 | 2023-02-10 | -283
DA22-056 | Lancaster Independent School District | 057-913 | 2022-04-01 | 2023-05-19 | -2428
DA22-057 | Brazos School for Inquiry & Creativity | 021-803 | 2022-04-01 | 2023-10-13 | -15761
DA22-058 | NYOS Charter School | 227-804 | 2022-04-01 | 2023-02-10 | -2236
DA22-059 | Salado Independent School District | 014-908 | 2022-04-01 | 2023-07-21 | 0
DA22-060 | Big Sandy Independent School District | 187-901 | 2022-04-01 | 2022-12-09 | 0
DA22-061 | Port Arthur Independent School District | 123-907 | 2022-04-01 | 2023-03-17 | -16200
DA22-062 | Mabank Independent School District | 129-905 | 2022-04-01 | 2023-02-10 | -5123
DA22-063 | Ferris Independent School District | 070-905 | 2022-04-01 | 2022-12-09 | 0
DA22-064 | Burkburnett Independent School District | 243-901 | 2022-04-01 | 2023-04-21 | -13268
DA22-065 | Devine Independent School District | 163-901 | 2022-04-01 | 2023-03-17 | -3607
DA22-066 | Bonham Independent School District | 074-903 | 2022-04-01 | 2023-02-10 | -167
DA22-067 | Electra Independent School District | 243-902 | 2022-04-01 | 2023-03-10 | -4696
DA22-068 | Atlanta Independent School District | 034-901 | 2022-04-01 | 2023-04-07 | 0
DA22-069 | North Texas Collegiate Academy | 061-802 | 2022-04-01 | 2023-02-10 | 0
DA22-070 | Tioga Independent School District | 091-907 | 2022-04-01 | 2022-11-18 | 0
DA22-071 | Pringle-Morse Consolidated Independent School District | 098-903 | 2022-04-01 | 2022-11-18 | 0
DA22-072 | Excellence in Leadership Academy | 108-809 | 2022-04-01 | 2023-01-06 | 0
DA22-073 | Montessori For All | 227-826 | 2022-04-01 | 2022-12-09 | 0
DA22-074 | New Waverly Independent School District | 236-901 | 2022-04-01 | 2023-04-21 | 0
DA22-075 | Mineola Independent School District | 250-903 | 2022-04-01 | 2023-04-21 | 0
DA22-076 | Pearland Independent School District | 020-908 | 2022-04-01 | 2023-02-10 | -1739

## Steps-FY21
Compliance and | Step | Description | Responsibility | Electronic
Followup Reviews | Step 1 | Mail Engagement Letters | Manager | Mailed
| Step 2 | Receive Phase 1 Docs (Questionnaire) | Auditor III
| Step 3 | Request Phase 2 Docs (Student Sample) | Auditor III | Justin Jons
| Step 4 | Receive Phase 2 Docs (Student Sample) | Auditor III | Christina Page
| Step 5 | Analyze Docs and Complete Workpaper Review | Auditor III | Matt Kabanuck
| Step 6 | Complete Prelim Report and Route for Review | Auditor III | John Munoz
| Step 7 | First Review Complete and Route for Second Review | Auditor IV | Yang Yang
| Step 8 | Second Review Complete and Route for Mailing | Manager
| Step 9 | Mail Prelim Report | Auditor IV | Tam Mai
| Step 10 | Receive Response/CAP | Auditor III | Eric Herring
| Step 11 | Analyze Response/CAP and Update Workpapers as Needed | Auditor III
| Step 12 | Complete Final Report and Route for Review | Auditor III | Email
| Step 13 | First Review Complete and Route for Second Review | Auditor IV | Phone Message
| Step 14 | Second Review Complete and Route for Mailing | Manager
| Step 15 | Mail Final Report | Auditor IV | Electronic
| Step 16 | Scan Documents into Alfresco and File Audit Folder | Auditor IV | Mailed
Desk Audits | Step | Description | Responsibility
| Step 1 | Mail Engagement Letters | Manager
| Step 2 | Receive Documentation from LEA | Auditor III
| Step 3a | Analyze Docs and Complete Dual Attendance Query | Auditor III
| Step 3b | Analyze Docs and Complete Kinder Under 5 Query | Auditor III
| Step 3c | Analyze Docs and Complete EE No Sped Query | Auditor III
| Step 3d | Analyze Docs and Complete EE Speech Only Query | Auditor III
| Step 3e | Analyze Docs and Complete EE Mainstream Query | Auditor III
| Step 3f | Analyze Docs and Complete PRS Query | Auditor III
| Step 4 | Complete Prelim Report and Route for Review | Auditor III
| Step 5a | Return to Auditor for Corrections | Auditor IV
| Step 5b | Corrections Made, Re-Route for First Review | Auditor III
| Step 5c | First Review Complete and Route for Second Review | Auditor IV
| Step 6 | Second Review Complete and Route for Mailing | Manager
| Step 7 | Mail Prelim Report | Auditor IV
| Step 8 | Receive Response/CAP | Auditor III
| Step 9 | Analyze Response/CAP and Apply Revisions as Needed/Add CAP to Folder | Auditor III
| Step 10 | Complete Final Report and Route for Review | Auditor III
| Step 11 | First Review Complete and Route for Second Review | Auditor IV
| Step 12 | Second Review Complete and Route for Mailing | Manager
| Step 13 | Mail Final Report | Auditor IV
| Step 14 | Scan Documents into Alfresco | Auditor IV
| Step 15 | Submit Audit Adjustments to State Funding | Auditor IV
| Step 16 | Receive Actual Audit Adjustments from State Funding | Auditor IV
| Step 17 | Finalize and Close Electronic Working File and Move to Electronic File Cabinet | Auditor IV

## CR21
Review Number | LEA Name | CDN | Step 1 | Step 15
CR21-001 | Betty M. Condra School for Education Innovation | 152-806 | 2020-11-06 | 2021-11-05
CR21-002 | Bloom Academy Charter School | 101-875 | 2020-11-06 | 2021-05-14
CR21-003 | Reve Preparatory Charter School | 101-876 | 2020-11-06 | 2021-06-11
CR21-004 | Waco Charter School | 161-801 | 2020-11-06 | 2021-09-10
CR21-005 | DeSoto ISD | 057-906 | 2020-11-06 | 2021-11-12
CR21-006 | Canutillo ISD | 071-907 | 2020-11-06 | 2021-07-30
CR21-007 | Anthony ISD | 071-906 | 2020-11-06 | 2021-07-02
CR21-008 | Tornillo ISD | 071-908 | 2020-11-06 | 2021-10-08
CR21-009 | San Elizario ISD | 071-904 | 2020-11-06 | 2021-10-22
CR21-010 | Uvalde CISD | 232-903 | 2020-11-06 | 2021-08-31
CR21-011 | Buckholts ISD | 166-907 | 2020-11-06 | 2021-07-23
CR21-012 | Amigos Por Vida-Friends for Life Public Charter School | 101-819 | 2020-11-06 | 2021-05-28
CR21-013 | Falls City ISD | 128-904 | 2020-11-06 | 2021-07-02
CR21-014 | Nazareth ISD | 035-903 | 2020-11-06 | 2021-10-01
CR21-015 | Lindsay ISD | 049-907 | 2020-11-06 | 2021-04-09
CR21-016 | Ezzell ISD | 143-906 | 2020-11-06 | 2021-05-28
CR21-017 | Iredell ISD | 018-906 | 2020-11-06 | 2021-04-09
CR21-018 | Vanguard Academy | 108-808 | 2020-11-06 | 2021-10-01
CR21-019 | Sundown ISD | 110-907 | 2020-11-06 | 2021-06-11
CR21-020 | Windthorst ISD | 005-904 | 2020-11-06 | 2021-05-28
CR21-021 | Sunnyvale ISD | 057-919 | 2020-11-06 | 2021-05-21
CR21-022 | Groom ISD | 033-901 | 2020-11-06 | 2021-05-07
CR21-023 | Shiner ISD | 143-903 | 2020-11-06 | 2021-07-02
CR21-024 | Devers ISD | 146-903 | 2020-11-06 | 2021-06-25
CR21-025 | Positive Solutions Charter School | 015-814 | 2020-11-06 | 2021-05-21
CR21-026 | Texas Serenity Academy | 170-801 | 2020-11-06 | 2021-07-16
CR21-027 | Benavides ISD | 066-901 | 2020-11-06 | 2021-05-28
CR21-028 | Runge ISD | 128-903 | 2020-11-06 | 2021-06-04
CR21-029 | Trinity ISD | 228-903 | 2020-11-06 | 2021-04-14
CR21-030 | Zavalla ISD | 003-906 | 2020-11-06 | 2021-11-05
CR21-031 | Crystal City ISD | 254-901 | 2020-11-06 | 2021-07-16
CR21-032 | Bexar County Academy | 015-809 | 2020-11-06 | 2022-01-07
CR21-033 | Aransas Pass ISD | 205-901 | 2020-11-06 | 2021-07-09
CR21-034 | Cotton Center ISD | 095-902 | 2020-11-06 | 2021-06-25
CR21-035 | Waelder ISD | 089-905 | 2020-11-06 | 2021-07-23
CR21-036 | Aransas County ISD | 004-901 | 2020-11-06 | 2021-06-25
CR21-037 | Shamrock ISD | 242-902 | 2020-11-06 | 2021-10-22
CR21-038 | Elkhart ISD | 001-903 | 2020-11-06 | 2021-08-04
CR21-039 | Frankston ISD | 001-904 | 2020-11-06 | 2021-07-30
CR21-040 | Neches ISD | 001-906 | 2020-11-06 | 2021-05-14
CR21-041 | Pineywoods Community Academy | 003-901 | 2020-11-06 | 2022-02-11
CR21-042 | Hudson ISD | 003-902 | 2020-11-06 | 2021-08-04
CR21-043 | Lufkin ISD | 003-903 | 2020-11-06 | 2021-08-04
CR21-044 | Huntington ISD | 003-904 | 2020-11-06 | 2021-05-07
CR21-045 | Diboll ISD | 003-905 | 2020-11-06 | 2021-10-01
CR21-046 | Central ISD | 003-907 | 2020-11-06 | 2021-06-04
CR21-047 | Archer City ISD | 005-901 | 2020-11-06 | 2021-06-11
CR21-048 | Claude ISD | 006-902 | 2020-11-06 | 2021-05-07
CR21-049 | Bellville ISD | 008-901 | 2020-11-06 | 2021-07-23
CR21-050 | Pleasanton ISD | 007-905 | 2020-11-06 | 2021-10-29
CR21-051 | Brazos ISD | 008-903 | 2020-11-06 | 2021-08-20

## F21
Review Number | LEA Name | CDN | Step 1 | Step 15
F21-001 | White Settlement ISD | 220-920 | 2020-11-06 | 2021-09-10
F21-002 | Bay City ISD | 158-901 | 2020-11-06 | 2021-10-22
F21-003 | New Caney ISD | 170-908 | 2020-11-06 | 2021-03-12
F21-004 | Prosper ISD | 043-912 | 2020-11-06 | 2021-05-07
F21-005 | Little Elm ISD | 061-914 | 2020-11-06 | 2021-06-25
F21-006 | Kerrville ISD | 133-903 | 2020-11-06 | 2021-10-22
F21-007 | Lamar CISD | 079-901 | 2020-11-06 | 2021-05-07
F21-008 | Navasota ISD | 093-904 | 2020-11-06 | 2021-09-10
F21-009 | Leadership Prep School | 061-804 | 2020-11-06 | 2021-08-04

## DA21
Review Number | LEA Name | CDN | Step 1 | Step 13 | Adjustment Amount
DA21-001 | University of Texas University Charter School | 227-806 | 2021-03-26 | 2022-05-20 | -12069
DA21-002 | KIPP Texas Public Schools | 227-820 | 2021-03-26 | 2021-07-23 | 0
DA21-003 | Brooks Academies of Texas | 015-830 | 2021-03-26 | 2021-07-09 | 0
DA21-004 | Mathis Independent School District | 205-904 | 2021-03-26 | 2021-10-22 | -6584
DA21-005 | Bartlett Independent School District | 014-902 | 2021-03-26 | 2021-04-23 | 0
DA21-006 | Southwest Preparatory School | 015-807 | 2021-03-26 | 2022-05-13 | -4731
DA21-007 | Axtell Independent School District | 161-918 | 2021-03-26 | 2021-04-23 | 0
DA21-008 | Meridian World School LLC | 246-801 | 2021-03-26 | 2021-11-05 | 0
DA21-009 | Calallen Independent School District | 178-903 | 2021-03-26 | 2021-11-12 | 0
DA21-010 | Abilene Independent School District | 221-901 | 2021-03-26 | 2022-06-24 | -4165
DA21-011 | Sinton Independent School District | 205-906 | 2021-03-26 | 2021-10-01 | 361
DA21-012 | Great Hearts Texas | 015-835 | 2021-03-26 | 2021-05-21 | 0
DA21-013 | Seguin Independent School District | 094-901 | 2021-03-26 | 2022-05-13 | -7878
DA21-014 | Hallsville Independent School District | 102-904 | 2021-03-26 | 2021-11-12 | -732
DA21-015 | West Oso Independent School District | 178-915 | 2021-03-26 | 2022-03-04 | -7707
DA21-016 | Premont Independent School District | 125-905 | 2021-03-26 | 2021-08-04 | 0
DA21-017 | Bob Hope School | 123-807 | 2021-03-26 | 2021-11-19 | -1347
DA21-018 | Killeen Independent School District | 014-906 | 2021-03-26 | 2022-07-22 | -9913
DA21-019 | Sherman Independent School District | 091-906 | 2021-03-26 | 2022-06-24 | -65035
DA21-020 | Georgetown Independent School District | 246-904 | 2021-03-26 | 2022-07-01 | -5628
DA21-021 | Flour Bluff Independent School District | 178-914 | 2021-03-26 | 2022-06-24 | -2241
DA21-022 | Rio Grande City Grulla Independent School District | 214-901 | 2021-03-26 | 2022-07-29 | -3077
DA21-023 | Galveston Independent School District | 084-902 | 2021-03-26 | 2022-05-13 | -10745
DA21-024 | Harmony Science Academy (San Antonio) | 015-828 | 2021-03-26 | 2021-10-08 | -4985
DA21-025 | Newman International Academy of Arlington | 220-817 | 2021-03-26 | 2022-02-11 | -3733
DA21-026 | Village Tech Schools | 057-847 | 2021-03-26 | 2021-07-09 | -6488
DA21-027 | Kingsville Independent School District | 137-901 | 2021-03-26 | 2021-08-31 | -3215
DA21-028 | Wichita Falls Independent School District | 243-905 | 2021-03-26 | 2022-12-30 | -126261
DA21-029 | Promesa Public Schools | 227-824 | 2021-03-26 | 2021-06-17 | -304
DA21-030 | Belton Independent School District | 014-903 | 2021-03-26 | 2021-12-03 | -2783
DA21-031 | Ingleside Independent School District | 205-903 | 2021-03-26 | 2021-12-03 | -18656
DA21-032 | Hooks Independent School District | 019-902 | 2021-03-26 | 2021-07-02 | -1862
DA21-033 | Community Independent School District | 043-918 | 2021-03-26 | 2021-12-03 | -1480
DA21-034 | Harmony School of Science - Houston | 101-862 | 2021-03-26 | 2021-06-25 | -3085
DA21-035 | Dumas Independent School District | 171-901 | 2021-03-26 | 2021-10-01 | -13995
DA21-036 | McDade Independent School District | 011-905 | 2021-03-26 | 2021-09-10 | -435
DA21-037 | Santa Anna Independent School District | 042-903 | 2021-03-26 | 2021-08-31 | -4106
DA21-038 | Evant Independent School District | 050-901 | 2021-03-26 | 2021-06-25 | -938
DA21-039 | Education Center International Academy | 057-833 | 2021-03-26 | 2021-05-14 | -3701
DA21-040 | Golden Rule Charter School | 057-835 | 2021-03-26 | 2021-06-11 | -3733
DA21-041 | Carrizo Springs Consolidated Independent School District | 064-903 | 2021-03-26 | 2022-04-15 | -3198
DA21-042 | Petersburg Independent School District | 095-904 | 2021-03-26 | 2021-04-23 | 0
DA21-043 | Raul Yzaguirre Schools for Success | 101-806 | 2021-03-26 | 2021-05-28 | -735
DA21-044 | Dayton Independent School District | 146-902 | 2021-03-26 | 2021-07-16 | -602
DA21-045 | Hardin Independent School District | 146-904 | 2021-03-26 | 2021-11-19 | -39
DA21-046 | Priddy Independent School District | 167-904 | 2021-03-26 | 2021-10-22 | 2
DA21-047 | Presidio Independent School District | 189-902 | 2021-03-26 | 2021-10-22 | -1594
DA21-048 | East Fort Worth Montessori Academy | 220-811 | 2021-03-26 | 2021-05-07 | 0
DA21-049 | Kennedale Independent School District | 220-914 | 2021-03-26 | 2021-09-17 | -4845
DA21-050 | La Pryor Independent School District | 254-902 | 2021-03-26 | 2021-10-01 | -3954
DA21-051 | Eagle Mountain-Saginaw Independent School District | 220-918 | 2021-03-26 | 2022-06-10 | -103546
DA21-052 | Midland Independent School District | 165-901 | 2021-03-26 | 2022-07-29 | -2122
DA21-053 | Wimberley Independent School District | 105-905 | 2021-03-26 | 2022-04-01 | -321
DA21-054 | Goose Creek Consolidated Independent School District | 101-911 | 2021-03-26 | 2022-10-14 | -3432
DA21-055 | Forney Independent School District | 129-902 | 2021-03-26 | 2022-05-13 | -6958
DA21-056 | Liberty Independent School District | 146-906 | 2021-03-26 | 2021-04-14 | 0
DA21-057 | Canyon Independent School District | 191-901 | 2021-03-26 | 2022-02-11 | -493
DA21-058 | Burleson Independent School District | 126-902 | 2021-03-26 | 2022-01-14 | -3386
DA21-059 | La Vernia Independent School District | 247-903 | 2021-03-26 | 2021-11-19 | -2790
DA21-060 | Beaumont Independent School District | 123-910 | 2021-03-26 | 2022-01-21 | -11820
DA21-061 | Chapel Hill Independent School District | 212-909 | 2021-03-26 | 2022-04-22 | -18013
DA21-062 | Crowley Independent School District | 220-912 | 2021-03-26 | 2022-04-15 | -14114
DA21-063 | Eanes Independent School District | 227-909 | 2021-03-26 | 2022-04-01 | -15002
DA21-064 | Melissa Independent School District | 043-908 | 2021-03-26 | 2022-03-04 | -5364
DA21-065 | Denver City Independent School District | 251-901 | 2021-03-26 | 2021-10-08 | -341
DA21-066 | Crosby Independent School District | 101-906 | 2021-03-26 | 2022-04-01 | -282
DA21-067 | Sheldon Independent School District | 101-924 | 2021-03-26 | 2022-06-24 | -2321
DA21-068 | Tomball Independent School District | 101-921 | 2021-03-26 | 2021-07-16 | -963
DA21-069 | New Boston Independent School District | 019-905 | 2021-03-26 | 2022-02-11 | 0
DA21-070 | Tulia Independent School District | 219-903 | 2021-03-26 | 2021-06-04 | -330
DA21-071 | Lindale Independent School District | 212-903 | 2021-03-26 | 2021-11-12 | -1745
DA21-072 | Fort Sam Houston Independent School District | 015-914 | 2021-03-26 | 2021-04-23 | 0
DA21-073 | Hardin-Jefferson Independent School District | 100-905 | 2021-03-26 | 2021-05-14 | -2185
DA21-074 | Sabine Pass Independent School District | 123-913 | 2021-03-26 | 2021-10-22 | -3709
DA21-075 | San Felipe-Del Rio Consolidated Independent School District | 233-901 | 2021-03-26 | 2022-05-20 | -15305
DA21-076 | Port Neches-Groves Independent School District | 123-908 | 2021-03-26 | 2021-11-12 | -653
DA21-077 | Longview Independent School District | 092-903 | 2021-03-26 | 2022-04-01 | -7843
DA21-078 | Elgin Independent School District | 011-902 | 2021-03-26 | 2022-05-27 | -968
DA21-079 | Cross Plains Independent School District | 030-901 | 2021-03-26 | 2022-01-14 | 0
DA21-080 | Navarro Independent School District | 094-903 | 2021-03-26 | 2022-04-01 | -10534
DA21-081 | Hull-Daisetta Independent School District | 146-905 | 2021-03-26 | 2021-08-31 | -14592
DA21-082 | Chico Independent School District | 249-904 | 2021-03-26 | 2021-11-19 | -5350
DA21-083 | Decatur Independent School District | 249-905 | 2021-03-26 | 2021-07-09 | -6246
DA21-084 | Liberty Hill Independent School District | 246-908 | 2021-03-26 | 2022-03-04 | -2637
DA21-085 | Wylie Independent School District | 221-912 | 2021-03-26 | 2022-05-13 | -6865
DA21-086 | Wills Point Independent School District | 234-907 | 2021-03-26 | 2021-10-01 | -1852
DA21-087 | Jarrell Independent School District | 246-907 | 2021-03-26 | 2022-02-11 | -3210
DA21-088 | Alvarado Independent School District | 126-901 | 2021-03-26 | 2021-10-08 | -7989
DA21-089 | Schulenburg Independent School District | 075-903 | 2021-03-26 | 2022-04-08 | -5036
DA21-090 | Livingston Independent School District | 187-907 | 2021-03-26 | 2022-07-01 | -1270
DA21-091 | Detroit Independent School District | 194-905 | 2021-03-26 | 2021-06-11 | 0
DA21-092 | Carroll Independent School District | 220-919 | 2021-03-26 | 2021-06-04 | -765
DA21-093 | Hutto Independent School District | 246-906 | 2021-03-26 | 2022-04-01 | -989
DA21-094 | Academy Independent School District | 014-901 | 2021-03-26 | 2021-04-23 | -659
DA21-095 | Hondo Independent School District | 163-904 | 2021-03-26 | 2021-05-28 | -7351
DA21-096 | Tatum Independent School District | 201-910 | 2021-03-26 | 2021-07-30 | -29
DA21-097 | Graham Independent School District | 252-901 | 2021-03-26 | 2021-08-31 | -524
DA21-098 | Holland Independent School District | 014-905 | 2021-03-26 | 2021-10-01 | -3296
DA21-099 | La Grange Independent School District | 075-902 | 2021-03-26 | 2021-09-10 | -1190
DA21-100 | Athens Independent School District | 107-901 | 2021-03-26 | 2021-10-01 | -14446
DA21-101 | Hillsboro Independent School District | 109-904 | 2021-03-26 | 2021-10-22 | -2329
DA21-102 | Latexo Independent School District | 113-905 | 2021-03-26 | 2021-08-20 | -2042
DA21-103 | Kenedy Independent School District | 128-902 | 2021-03-26 | 2021-06-17 | -4918
DA21-104 | Stanton Independent School District | 156-902 | 2021-03-26 | 2021-07-16 | -1169
DA21-105 | Crawford Independent School District | 161-901 | 2021-03-26 | 2022-01-07 | -2001
DA21-106 | Garrison Independent School District | 174-903 | 2021-03-26 | 2021-07-16 | -4219
DA21-107 | Strawn Independent School District | 182-905 | 2021-03-26 | 2021-10-01 | -3796
DA21-108 | Clarksville Independent School District | 194-904 | 2021-03-26 | 2021-11-12 | -7356
DA21-109 | Ballinger Independent School District | 200-901 | 2021-03-26 | 2021-04-14 | 0
DA21-110 | Jim Ned Consolidated Independent School District | 221-911 | 2021-03-26 | 2021-10-01 | -412
DA21-111 | Lake Travis Independent School District | 227-913 | 2021-03-26 | 2021-08-31 | -1723
DA21-112 | Willis Independent School District | 170-904 | 2021-03-26 | 2022-04-08 | -1827
DA21-113 | Highland Park Independent School District | 057-911 | 2021-03-26 | 2022-01-07 | 0
DA21-114 | Anna Independent School District | 043-902 | 2021-03-26 | 2022-02-11 | -2184
DA21-115 | South San Antonio Independent School District | 015-908 | 2021-03-26 | 2022-01-07 | -4644
DA21-116 | Sanger Independent School District | 061-908 | 2021-03-26 | 2021-08-04 | -366
DA21-117 | Ponder Independent School District | 061-906 | 2021-03-26 | 2022-01-07 | -6211
DA21-118 | College Station Independent School District | 021-901 | 2021-03-26 | 2022-05-13 | -1885
DA21-119 | Springtown Independent School District | 184-902 | 2021-03-26 | 2021-12-03 | -3043
DA21-120 | Stafford Municipal School District | 079-910 | 2021-03-26 | 2022-05-13 | -294
DA21-121 | Aubrey Independent School District | 061-907 | 2021-03-26 | 2021-07-23 | 0
DA21-122 | Friendswood Independent School District | 084-911 | 2021-03-26 | 2021-11-05 | 0
DA21-123 | Whitesboro Independent School District | 091-909 | 2021-03-26 | 2021-10-08 | 0
DA21-124 | Brock Independent School District | 184-909 | 2021-03-26 | 2022-01-07 | -1736
DA21-125 | Bushland Independent School District | 188-904 | 2021-03-26 | 2021-06-11 | 0
DA21-126 | Albany Independent School District | 209-901 | 2021-03-26 | 2021-07-23 | 0
DA21-127 | Midway Independent School District | 161-903 | 2021-03-26 | 2022-01-07 | -823
DA21-128 | Cedar Hill Independent School District | 057-904 | 2021-03-26 | 2022-04-01 | -16613
DA21-129 | Big Spring Independent School District | 114-901 | 2021-03-26 | 2022-01-21 | 179
DA21-130 | Hamshire-Fannett Independent School District | 123-914 | 2021-03-26 | 2021-11-12 | -5822
DA21-131 | Pharr-San Juan-Alamo Independent School District | 108-909 | 2021-03-26 | 2022-07-08 | -16194
DA21-132 | Spring Branch Independent School District | 101-920 | 2021-03-26 | 2022-07-22 | -3699
DA21-133 | Triumph Public High Schools-Rio Grande Valley | 108-804 | 2021-03-26 | 2022-07-29 | -1148
DA21-134 | Triumph Public High Schools-Laredo | 240-801 | 2021-03-26 | 2022-07-08 | -2662
DA21-135 | Harlandale Independent School District | 015-904 | 2021-03-26 | 2022-04-01 | -2991
DA21-136 | McAllen Independent School District | 108-906 | 2021-03-26 | 2022-01-07 | -1083
DA21-137 | Cleveland Independent School District | 146-901 | 2021-03-26 | 2022-01-14 | -60
DA21-138 | Clint Independent School District | 071-901 | 2021-03-26 | 2021-09-10 | -1416
DA21-139 | George I. Sanchez Charter | 101-804 | 2021-03-26 | 2021-09-10 | -1526
DA21-140 | Waxahachie Independent School District | 070-912 | 2021-03-26 | 2022-01-07 | -213
DA21-141 | El Campo Independent School District | 241-903 | 2021-03-26 | 2022-04-01 | -1712
DA21-142 | Snyder Independent School District | 208-902 | 2021-03-26 | 2022-02-11 | -10255
DA21-143 | Corsicana Independent School District | 175-903 | 2021-03-26 | 2022-01-07 | -2885
DA21-144 | YES Prep Public Schools Inc. | 101-845 | 2021-03-26 | 2022-05-20 | -10040
DA21-145 | Edcouch-Elsa Independent School District | 108-903 | 2021-03-26 | 2022-06-24 | -8354
DA21-146 | La Porte Independent School District | 101-916 | 2021-03-26 | 2021-08-20 | -7734
DA21-147 | Mercedes Independent School District | 108-907 | 2021-03-26 | 2021-08-04 | -1930
DA21-148 | Lockhart Independent School District | 028-902 | 2021-03-26 | 2021-11-12 | -747

## Steps-FY20
Compliance and | Step | Description | Responsibility | Electronic
Followup Reviews | Step 1 | Mail Engagement Letters | Manager | Mailed
| Step 2 | Receive Phase 1 Docs (Questionnaire) | Auditor III
| Step 3 | Request Phase 2 Docs (Student Sample) | Auditor III | Justin Jons
| Step 4 | Receive Phase 2 Docs (Student Sample) | Auditor III | Christina Page
| Step 5 | Analyze Docs and Complete Workpaper Review | Auditor III | Matt Kabanuck
| Step 6 | Complete Prelim Report and Route for Review | Auditor III | John Munoz
| Step 7 | First Review Complete and Route for Second Review | Auditor IV | Yang Yang
| Step 8 | Mail Prelim Report | Auditor IV | Tam Mai
| Step 9 | Receive Response/CAP | Auditor III | Eric Herring
| Step 10 | Analyze Response/CAP and Update Workpapers as Needed | Auditor III
| Step 11 | Complete Final Report and Route for Review | Auditor III | Email
| Step 12 | First Review Complete and Route for Second Review | Auditor IV | Phone Message
| Step 13 | Mail Final Report | Auditor IV
| Step 14 | Scan Documents into Alfresco and File Audit Folder | Auditor IV
Desk Audits | Step | Description | Responsibility
| Step 1 | Mail Engagement Letters | Manager
| Step 2 | Receive Documentation from LEA | Auditor III
| Step 3a | Analyze Docs and Complete Dual Attendance Query | Auditor III
| Step 3b | Analyze Docs and Complete Kinder Under 5 Query | Auditor III
| Step 3c | Analyze Docs and Complete EE No Sped Query | Auditor III
| Step 3d | Analyze Docs and Complete EE Speech Only Query | Auditor III
| Step 3e | Analyze Docs and Complete EE Mainstream Query | Auditor III
| Step 3f | Analyze Docs and Complete PRS Query | Auditor III
| Step 4 | Complete Prelim Report and Route for Review | Auditor III
| Step 5a | First Review Complete and Route for Second Review | Auditor IV
| Step 5b | Return to Auditor for Corrections | Auditor IV
| Step 5c | Corrections Made, Re-Route for First Review | Auditor III
| Step 6 | Second Review Complete and Route for Mailing | Manager
| Step 7 | Mail Prelim Report | Auditor IV
| Step 8 | Receive Response/CAP | Auditor III
| Step 9 | Analyze Response/CAP and Apply Revisions as Needed/Add CAP to Folder | Auditor III
| Step 10 | Complete Final Report and Route for Review | Auditor III
| Step 11 | First Review Complete and Route for Second Review | Auditor IV
| Step 12 | Second Review Complete and Route for Mailing | Manager
| Step 13 | Mail Final Report | Auditor IV
| Step 14 | Submit Audit Adjustments to State Funding | Auditor IV
| Step 15 | Receive Actual Audit Adjustments from State Funding | Auditor IV
| Step 16 | Scan Documents into Alfresco and File Audit Folder | Auditor IV

## F20
Review Number | LEA Name | CDN | Step 1 | Step 13
F20-001 | El Paso Independent School District | 071-902 | 2019-11-25 | 2020-12-29
F20-002 | Victoria Independent School District | 235-902 | 2019-11-25 | 2020-05-29
F20-003 | Como-Pickton Consolidated Independent School District | 112-908 | 2019-11-25 | 2020-02-24
F20-004 | Channelview Independent School District | 101-905 | 2019-11-25 | 2020-07-28
F20-005 | Everman Independent School District | 220-904 | 2019-11-25 | 2020-07-28

## CR20
Review Number | LEA Name | CDN | Step 1 | Step 13
CR20-001 | Bridgeway Preparatory Academy | 057-851 | 2019-11-25 | 2020-11-20
CR20-002 | Etoile Academy Charter School | 101-872 | 2019-11-25 | 2020-05-29
CR20-003 | Lake Granbury Academy | 111-801 | 2019-11-25 | 2020-07-16
CR20-004 | Legacy School of Sport Sciences | 101-874 | 2019-11-25 | 2020-08-12
CR20-005 | Valor Public Schools | 227-829 | 2019-11-25 | 2020-10-09
CR20-006 | Yellowstone College Preparatory | 101-873 | 2019-11-25 | 2020-07-06
CR20-007 | Holliday Independent School District | 005-902 | 2019-11-25 | 2020-05-29
CR20-008 | Patton Springs Independent School District | 063-906 | 2019-11-25 | 2020-05-29
CR20-009 | Savoy Independent School District | 074-911 | 2019-11-25 | 2020-11-24
CR20-010 | Gruver Independent School District | 098-901 | 2019-11-25 | 2020-03-31
CR20-011 | Spring Creek Independent School District | 117-907 | 2019-11-25 | 2020-07-28
CR20-012 | Ehrhart School | 123-805 | 2019-11-25 | 2020-03-31
CR20-013 | Texhoma Independent School District | 211-901 | 2019-11-25 | 2021-01-15
CR20-014 | Poth Independent School District | 247-904 | 2019-11-25 | 2020-06-26
CR20-015 | Slocum Independent School District | 001-909 | 2019-11-25 | 2020-06-26
CR20-016 | La Academia de Estrellas | 057-839 | 2019-11-25 | 2020-06-26
CR20-017 | Round Top-Carmine Independent School District | 075-908 | 2019-11-25 | 2020-12-11
CR20-018 | Bells Independent School District | 091-901 | 2019-11-25 | 2020-03-31
CR20-019 | Houston Gateway Academy Inc. | 101-828 | 2019-11-25 | 2020-08-31
CR20-020 | Lorena Independent School District | 161-907 | 2019-11-25 | 2020-06-26

## DA20
Review Number | LEA Name | CDN | Step 1 | Step 13 | Adjustment Amount
DA20-001 | Raven School | 236-801 | 2020-06-05 | 2021-03-12 | -422
DA20-002 | McKinney ISD | 043-907 | 2020-06-05 | 2020-11-06 | -3663
DA20-003 | Waco ISD | 161-914 | 2020-06-05 | 2020-12-04 | -86320
DA20-004 | Iraan-Sheffield ISD | 186-903 | 2020-06-05 | 2020-08-07 | 0
DA20-005 | Universal Academy | 057-808 | 2020-06-05 | 2020-10-09 | -17984
DA20-006 | Texas College Preparatory Academies | 221-801 | 2020-06-05 | 2020-09-30 | -18379
DA20-007 | Arlington ISD | 220-901 | 2020-06-05 | 2021-02-04 | -35113
DA20-008 | George Gervin Academy | 015-802 | 2020-06-05 | 2020-09-25 | -2920
DA20-009 | Houston Gateway Academy Inc. | 101-828 | 2020-06-05 | 2020-09-30 | -3427
DA20-010 | Corpus Christi ISD | 178-904 | 2020-06-05 | 2020-12-29 | -10255
DA20-011 | Donna ISD | 108-902 | 2020-06-05 | 2020-09-30 | -18966
DA20-012 | Galena Park ISD | 101-910 | 2020-06-05 | 2020-09-30 | -1166
DA20-013 | Laredo ISD | 240-901 | 2020-06-05 | 2020-10-16 | -12949
DA20-014 | Fort Bend ISD | 079-907 | 2020-06-05 | 2021-04-23 | -46250
DA20-015 | Katy ISD | 101-914 | 2020-06-05 | 2020-11-24 | -2352
DA20-016 | Grand Prairie ISD | 057-910 | 2020-06-05 | 2020-10-09 | -19469
DA20-017 | Mansfield ISD | 220-908 | 2020-06-05 | 2020-09-30 | -14056
DA20-018 | Odem-Edroy ISD | 205-905 | 2020-06-05 | 2020-08-31 | -10522
DA20-019 | Klein ISD | 101-915 | 2020-06-05 | 2020-09-30 | -19770
DA20-020 | Lytle ISD | 007-904 | 2020-06-05 | 2020-08-13 | 0
DA20-021 | Terrell ISD | 129-906 | 2020-06-05 | 2020-09-25 | -4973
DA20-022 | Southside ISD | 015-917 | 2020-06-05 | 2020-12-04 | -57500
DA20-023 | Montgomery ISD | 170-903 | 2020-06-05 | 2020-09-30 | -12360
DA20-024 | Pecos-Barstow-Toyah ISD | 195-901 | 2020-06-05 | 2020-10-30 | -14691
DA20-025 | Humble ISD | 101-913 | 2020-06-05 | 2020-11-20 | -14931
DA20-026 | Little Cypress-Mauriceville CISD | 181-908 | 2020-06-05 | 2020-09-25 | -11298
DA20-027 | Nederland ISD | 123-905 | 2020-06-05 | 2020-09-30 | -2401
DA20-028 | Brazosport ISD | 020-905 | 2020-06-05 | 2020-09-25 | -18893
DA20-029 | Willis ISD | 170-904 | 2020-06-05 | 2020-08-21 | -1370
DA20-030 | Tuloso-Midway ISD | 178-912 | 2020-06-05 | 2020-11-06 | -184
DA20-031 | Del Valle ISD | 227-910 | 2020-08-14 | 2021-04-09 | -26537
DA20-032 | Wayside Schools | 227-803 | 2020-08-14 | 2021-01-22 | -936
DA20-033 | Mullin ISD | 167-902 | 2020-08-14 | 2020-12-11 | Clean
DA20-034 | Inspire Academies | 015-808 | 2020-08-14 | 2020-09-25 | Clean
DA20-035 | Bastrop ISD | 011-901 | 2020-08-14 | 2020-11-24 | -6059
DA20-036 | Alamo Heights ISD | 015-901 | 2020-08-14 | 2021-01-29 | -16846
DA20-037 | Magnolia ISD | 170-906 | 2020-08-14 | 2021-04-09 | -6834
DA20-038 | Plainview ISD | 095-905 | 2020-08-14 | 2021-04-09 | -3583
DA20-039 | Temple ISD | 014-909 | 2020-08-14 | 2021-01-15 | -3965
DA20-040 | Grapevine-Colleyville ISD | 220-906 | 2020-08-14 | 2021-03-05 | -9119
DA20-041 | Cleburne ISD | 126-903 | 2020-08-14 | 2021-02-26 | -6992
DA20-042 | Copperas Cove ISD | 050-910 | 2020-08-14 | 2020-11-06 | -269
DA20-043 | Andrews ISD | 002-901 | 2020-08-14 | 2020-11-06 | -17694
DA20-044 | Gilmer ISD | 230-902 | 2020-08-14 | 2020-12-04 | Clean
DA20-045 | Lackland ISD | 015-913 | 2020-08-14 | 2020-10-16 | Clean
DA20-046 | Waxahachie Faith Family Academy | 070-801 | 2020-08-14 | 2020-11-06 | -2332
DA20-047 | LaPoynor ISD | 107-910 | 2020-08-14 | 2020-11-06 | -6836
DA20-048 | Borger ISD | 117-901 | 2020-08-14 | 2020-12-04 | -257
DA20-049 | Castleberry ISD | 220-917 | 2020-08-14 | 2021-01-15 | -3411
DA20-050 | Charlotte ISD | 007-901 | 2020-08-14 | 2020-11-06 | -3225
DA20-051 | Randolph Field ISD | 015-906 | 2020-08-14 | 2020-09-25 | Clean
DA20-052 | Pleasant Grove ISD | 019-912 | 2020-08-14 | 2020-12-17 | -149
DA20-053 | Hubbard ISD | 019-913 | 2020-08-14 | 2020-10-09 | -7594
DA20-054 | Argyle ISD | 061-910 | 2020-08-14 | 2021-01-29 | -1156
DA20-055 | Burnham Wood Charter School District | 071-801 | 2020-08-14 | 2020-11-20 | -82
DA20-056 | Comfort ISD | 130-902 | 2020-08-14 | 2020-09-25 | -930
DA20-057 | Madisonville CISD | 154-901 | 2020-08-14 | 2020-12-29 | -7903
DA20-058 | Rice ISD | 175-911 | 2020-08-14 | 2020-09-25 | Clean
DA20-059 | New Diana ISD | 230-906 | 2020-08-14 | 2020-10-16 | Clean
DA20-060 | Northwest ISD | 061-911 | 2020-08-14 | 2020-12-11 | Clean
DA20-061 | Hurst-Euless-Bedford ISD | 220-916 | 2020-08-14 | 2021-03-12 | -2615
DA20-062 | Duncanville ISD | 057-907 | 2020-08-14 | 2021-03-12 | -1735
DA20-063 | Ennis ISD | 070-903 | 2020-08-14 | 2021-01-29 | -13610
DA20-064 | Whitehouse ISD | 212-906 | 2020-08-14 | 2021-05-14 | -102050
DA20-065 | Denton ISD | 061-901 | 2020-08-14 | 2021-06-25 | -66005
DA20-066 | Princeton ISD | 043-911 | 2020-08-14 | 2021-02-04 | -85714
DA20-067 | Lake Dallas ISD | 061-912 | 2020-08-14 | 2020-11-06 | -26058
DA20-068 | East Central ISD | 015-911 | 2020-08-14 | 2021-06-25 | -2285
DA20-069 | Azle ISD | 220-915 | 2020-08-14 | 2021-01-15 | -40
DA20-070 | Denison ISD | 091-903 | 2020-08-14 | 2020-12-29 | -984
DA20-071 | Royse City ISD | 199-902 | 2020-08-14 | 2021-01-22 | -2719
DA20-072 | Allen ISD | 043-901 | 2020-08-14 | 2020-12-29 | -10566
DA20-073 | Winfree Academy Charter Schools | 057-828 | 2020-08-14 | 2021-04-23 | -13644
DA20-074 | San Marcos CISD | 105-902 | 2020-08-14 | 2020-12-17 | -5332
DA20-075 | Eagle Pass ISD | 159-901 | 2020-08-14 | 2021-03-05 | -244
DA20-076 | Southwest ISD | 015-912 | 2020-08-14 | 2021-04-14 | -4078
DA20-077 | Hereford ISD | 059-901 | 2020-08-14 | 2020-12-29 | -2962

## Steps-Complaints
Complaint | Step | Description | Responsibility
Investigations | Step 1 | Complete Notification Letter(s) and Route for Review | Auditor IV
| Step 2 | Notification Letter Review Complete and Route for Mailing | Manager
| Step 3a | Mail Engagement Letter to LEA (Certified) | Auditor IV
| Step 3b | Mail Notification Letter to Complainant | Auditor IV
| Step 4 | Receive Documentation Requested in Engagement Letter | Auditor IV
| Step 5 | Analyze Docs and Complete Investigative Review | Auditor IV
| Step 6 | Complete Prelim Report and Route for Review | Auditor IV
| Step 7 | First Review Complete and Route for Mailing | Manager
| Step 8 | Mail Prelim Report (Certified) | Auditor IV
| Step 9 | Receive Response/CAP | Auditor IV
| Step 10 | Complete Final Report and Route for Review | Auditor IV
| Step 11 | First Review Complete and Route for Mailing | Manager
| Step 12 | Mail Final Report (Certified) | Auditor IV
| Step 13 | Scan Documents into Alfresco | Auditor IV
| Step 14 | Submit Adjustments to State Funding | Auditor IV
| Step 15 | Receive Actual Audit Adjustments from State Funding | Auditor IV
| Step 16 | Finalize and Close Electronic Working File and Move to Electronic File Cabinet | Auditor IV

## Complaints
Investigation Number | LEA Name | CDN | TEA Complaint # | Step 3a | Step 12 | Adjustment Amount | Days Elapsed from Engagement to Final | Days Elapsed from Acceptance to Notification
CC21-001 | Bremond ISD | 198-901 | ER2019-09-002 | 2021-01-22 | 2021-02-26 | N/A | 35 | N/A
CC21-002 | Edinburg CISD | 108-904 | INV2019-05-025 | 2021-01-22 | 2021-04-09 | N/A | 78 | N/A
CC21-003 | Fort Worth ISD | 220-905 | INV2019-06-064 | 2021-01-29 | 2021-11-05 | -33295 | 282 | N/A
|  |  | INV2020-12-061 | 2021-01-29 | 2021-10-22 | N/A | 267 | N/A
CC21-004 | Cumberland Academy | 212-801 | INV2019-10-028 | 2021-02-04 | 2021-02-26 | N/A | 22 | N/A
CC21-005 | Bexar County Academy | 015-809 | ER2020-12-001 | 2021-02-04 | 2021-11-05 | -709 | 275 | N/A
CC21-006 | Por Vida Academy | 015-801 | ER2020-09-001 | 2021-02-26 | 2022-01-14 | 0 | 323 | N/A
CC21-007 | Harmony School of Excellence | 101-858 | ER2020-11-006 | 2021-02-26 | 2021-05-07 | N/A | 71 | N/A
CC21-008 | George Gervin Academy | 015-802 | INV2018-04-080 | 2021-04-09 | 2021-11-05 | 27 | 211 | N/A
CC21-009 | Robstown ISD | 178-909 | INV2018-11-112 | 2021-04-14 | 2023-02-10 | -58643 | 667 | N/A
CC21-010 | Jean Massieu Academy | 057-819 | INV2021-04-021/ER2021-05-011 | 2021-04-23 | 2022-04-01 | -8294 | 342 | N/A
CC21-011 | Donna ISD | 108-902 | ER2018-04-005/ER2018-04-011 | 2021-05-07 | 2022-09-16 | N/A | 497 | N/A
CC21-012 | IDEA Public Schools | 108-807 | ER2018-05-011 | 2021-05-07 | 2022-03-04 | -320 | 301 | N/A
CC21-013 | IDEA Public Schools | 108-807 | INV2019-02-057 | 2021-05-21 | 2021-10-22 | N/A | 155 | N/A
CC21-014 | IDEA Public Schools | 108-807 | INV2019-04-151 | 2021-05-28 | 2022-02-11 | -26 | 259 | N/A
CC21-015 | Laredo ISD | 240-901 | INV2019-02-084 | 2021-06-04 | 2022-10-07 | -34728 | 490 | N/A
CC21-016 | Stanton ISD | 156-902 | ER2019-05-009 | 2021-06-04 | 2023-05-12 | -14556 | 707 | N/A
CC21-017 | Beta Academy | 101-870 | ER2021-06-004 | 2021-07-23 | 2022-09-02 | -2775 | 406 | #REF!
CC22-001 | Alice ISD | 125-901 | INV2022-06-127 | 2022-08-26 | 2022-12-30 | -43 | 126 | N/A
CC22-002 | Columbia-Brazoria ISD | 020-907 | INV2022-06-017 | 2022-08-26 | 2022-09-16 | N/A | 21 | 7
CC23-001 | Gonzales ISD | 089-901 | INV2023-10-077 | 2022-12-09 | 2023-02-10 | N/A | 63 | 2
CC23-002 | IDEA Public Schools | 108-807 | ER2023-12-005/SAO INTK000001992 | 2023-01-13 | 2023-08-11 | -10701 | 210 | 1
CC23-003 | Longview ISD | 092-903 | INV2023-03-028 | 2023-04-21 | 2023-06-09 | N/A | 49 | 4
CC23-004 | La Joya ISD | 108-912 | INV2023-06-035 | 2023-06-16 | 2024-05-24 | -2233 | 343 | 1
CC23-005 | Aldine ISD | 101-902 | IR2023-07-004 | 2023-08-11 |  |  |  | 2
CC24-001 | Beaumont ISD | 123-910 | INV2024-09-240 | 2023-11-10 | 2024-06-21 | -18703 | 224 | 1
CC24-002 | Burnham Wood Charter School District | 071-801 | ER2024-02-002 | 2024-03-29 | 2024-12-06 |  | 252 | 6
CC24-003 | San Antonio ISD | 015-907 | ER2024-05-004 | 2024-06-14 |  |  |  | 4

## Steps-FY23
Compliance and | Step | Description | Responsibility | Electronic | Electronic
Followup Reviews | Step 1 | Mail Engagement Letters | Manager | Mailed | Mailed
| Step 2 | Receive Phase 1 Docs (Questionnaire) | Auditor III
| Step 3 | Request Phase 2 Docs (Student Sample) | Auditor III
| Step 4 | Receive Phase 2 Docs (Student Sample) | Auditor III
| Step 5 | Analyze Docs and Complete Workpaper Review | Auditor III
| Step 6 | Complete Prelim Report and Route for Review | Auditor III
| Step 7 | First Review Complete and Route for Second Review | Auditor IV
| Step 8 | Second Review Complete and Route for Mailing | Manager
| Step 9 | Mail Prelim Report | Auditor IV
| Step 10 | Receive Response/CAP | Auditor III
| Step 11 | Analyze Response/CAP and Update Workpapers as Needed | Auditor III
| Step 12 | Complete Final Report and Route for Review | Auditor III
| Step 13 | First Review Complete and Route for Second Review | Auditor IV
| Step 14 | Second Review Complete and Route for Mailing | Manager
| Step 15 | Mail Final Report | Auditor IV
| Step 16 | Scan Documents into Alfresco and File Audit Folder | Auditor IV
| Step 17 | Finalize and Close Electronic Working File and Move to Electronic File Cabinet | Auditor IV
Desk Audits | Step | Description | Responsibility
| Step 1 | Mail Engagement Letters | Manager
| Step 2 | Receive Documentation from LEA | Auditor III
| Step 3a | Analyze Docs and Complete Kinder Under 5 Query | Auditor III
| Step 3b | Analyze Docs and Complete EE No Sped Query | Auditor III
| Step 3c | Analyze Docs and Complete EE Speech Only Query | Auditor III
| Step 3d | Analyze Docs and Complete Bilingual/ESL Query | Auditor III
| Step 3e | Analyze Docs and Complete PRS Query | Auditor III
| Step 4 | Complete Prelim Report and Route for Review | Auditor III
| Step 5a | Return to Auditor for Corrections | Auditor IV
| Step 5b | Corrections Made, Re-Route for First Review | Auditor III
| Step 5c | First Review Complete and Route for Second Review | Auditor IV
| Step 6 | Second Review Complete and Route for Mailing | Manager
| Step 7 | Mail Prelim Report | Auditor IV
| Step 8 | Receive Response/CAP | Auditor III
| Step 9 | Analyze Response/CAP and Apply Revisions as Needed/Add CAP to Folder | Auditor III
| Step 10 | Complete Final Report and Route for Review | Auditor III
| Step 11 | First Review Complete and Route for Second Review | Auditor IV
| Step 12 | Second Review Complete and Route for Mailing | Manager
| Step 13 | Mail Final Report | Auditor IV
| Step 14 | Scan Documents into Alfresco | Auditor IV
| Step 15 | Submit Audit Adjustments to State Funding | Auditor IV
| Step 16 | Receive Actual Audit Adjustments from State Funding | Auditor IV
| Step 17 | Finalize and Close Electronic Working File and Move to Electronic File Cabinet | Auditor IV
Calendar Audits | Step | Description | Responsibility
| Step 1 | Mail Engagement Letters | Auditor IV
| Step 2 | Receive Documentation from LEA | Auditor IV
| Step 3 | Analyze LEA Response and Complete Working Folder | Auditor IV
| Step 4 | Complete Prelim Report and Route for Review | Auditor IV
| Step 5 | First Review Complete and Route for Mailing | Manager
| Step 6 | Mail Prelim Report | Auditor IV
| Step 7 | Receive Response/CAP | Auditor IV
| Step 8 | Analyze Response/CAP and Update Workpapers as Needed | Auditor IV
| Step 9 | Complete Final Report and Route for Review | Auditor IV
| Step 10 | First Review Complete and Route for Mailing | Manager
| Step 11 | Mail Final Report | Auditor IV
| Step 12 | Scan Documents into Alfresco | Auditor IV
| Step 13 | Submit Audit Adjustments to State Funding | Auditor IV
| Step 14 | Receive Actual Audit Adjustments from State Funding | Auditor IV
| Step 15 | Finalize and Close Electronic Working File and Move to Electronic File Cabinet | Auditor IV

## DA23
Review Number | LEA Name | CDN | Step 1 | Step 13 | Adjustment Amount
DA23-001 | Arlington Independent School District | 220-901 | 2023-02-10 | 2024-03-22 | -30678
DA23-002 | Waco Independent School District | 161-914 | 2023-02-10 | 2023-11-10 | -26391
DA23-003 | Katy Independent School District | 101-914 | 2023-02-10 | 2024-02-02 | -12606
DA23-004 | Fort Bend Independent School District | 079-907 | 2023-02-10 | 2024-03-15 | -3556
DA23-005 | El Paso Academy | 071-804 | 2023-02-10 | 2023-09-29 | 0
DA23-006 | Klein Independent School District | 101-915 | 2023-02-10 | 2024-03-15 | -51391
DA23-007 | Galena Park Independent School District | 101-910 | 2023-02-10 | 2023-11-17 | -20716
DA23-008 | Corpus Christi Independent School District | 178-904 | 2023-02-10 | 2024-02-09 | 0
DA23-009 | Northwest Independent School District | 061-911 | 2023-02-10 | 2024-03-15 | -92419
DA23-010 | Donna Independent School District | 108-902 | 2023-02-10 | 2024-02-09 | -313
DA23-011 | Laredo Independent School District | 240-901 | 2023-02-10 | 2023-11-17 | -4332
DA23-012 | Humble Independent School District | 101-913 | 2023-02-10 | 2024-04-19 | -1172
DA23-013 | Denton Independent School District | 061-901 | 2023-02-10 | 2024-03-15 | -17052
DA23-014 | Pflugerville Independent School District | 227-904 | 2023-02-10 | 2024-04-05 | -13302
DA23-015 | Hays Consolidated Independent School District | 105-906 | 2023-02-10 | 2023-12-08 | -15784
DA23-016 | Grand Prairie Independent School District | 057-910 | 2023-02-10 | 2024-03-15 | -14844
DA23-017 | Weslaco Independent School District | 108-913 | 2023-02-10 | 2024-02-09 | -1549
DA23-018 | Del Valle Independent School District | 227-910 | 2023-02-10 | 2024-01-12 | -150
DA23-019 | Eagle Pass Independent School District | 159-901 | 2023-02-10 | 2023-11-17 | -3239
DA23-020 | Brazosport Independent School District | 020-905 | 2023-02-10 | 2024-01-12 | 0
DA23-021 | Duncanville Independent School District | 057-907 | 2023-02-10 | 2023-12-29 | -2332
DA23-022 | Cleburne Independent School District | 126-903 | 2023-02-10 | 2023-12-08 | -6059
DA23-023 | Temple Independent School District | 014-909 | 2023-02-10 | 2024-03-15 | -1560
DA23-024 | McKinney Independent School District | 043-907 | 2023-02-10 | 2024-02-02 | -35082
DA23-025 | Channelview Independent School District | 101-905 | 2023-02-10 | 2023-12-08 | 0
DA23-026 | Evolution Academy Charter School | 057-834 | 2023-02-10 | 2024-03-22 | 0
DA23-027 | Manor Independent School District | 227-907 | 2023-02-10 | 2024-02-09 | -995
DA23-028 | Nederland Independent School District | 123-905 | 2023-02-10 | 2023-12-08 | 0
DA23-029 | Southwest Independent School District | 015-912 | 2023-02-10 | 2023-11-17 | -171
DA23-030 | San Marcos Consolidated Independent School District | 105-902 | 2023-02-10 | 2024-02-09 | -2162
DA23-031 | Medina Valley Independent School District | 163-908 | 2023-02-10 | 2024-02-02 | -266
DA23-032 | Midlothian Independent School District | 070-908 | 2023-02-10 | 2024-03-15 | -6283
DA23-033 | Tyler Independent School District | 212-905 | 2023-02-10 | 2023-11-17 | -5577
DA23-034 | Texas City Independent School District | 084-906 | 2023-02-10 | 2024-03-15 | -347
DA23-035 | Webb Consolidated Independent School District | 240-904 | 2023-02-10 | 2024-03-15 | -65222
DA23-036 | Los Fresnos Consolidated Independent School District | 031-906 | 2023-02-10 | 2023-11-10 | 0
DA23-037 | Schertz-Cibolo-Universal City Independent School District | 094-902 | 2023-02-10 | 2023-12-29 | -1743
DA23-038 | Coppell Independent School District | 057-922 | 2023-02-10 | 2024-04-19 | -1
DA23-039 | Luling Independent School District | 028-903 | 2023-02-10 | 2024-02-02 | -23809
DA23-040 | Magnolia Independent School District | 170-906 | 2023-02-10 | 2024-03-15 | 0
DA23-041 | San Benito Consolidated Independent School District | 031-912 | 2023-02-10 | 2023-11-10 | -8555
DA23-042 | New Braunfels Independent School District | 046-901 | 2023-02-10 | 2024-03-15 | -7471
DA23-043 | Crockett Independent School District | 113-901 | 2023-02-10 | 2023-12-29 | -4473
DA23-044 | Allen Independent School District | 043-901 | 2023-02-10 | 2024-05-17 | -8891
DA23-045 | Kermit Independent School District | 248-901 | 2023-02-10 | 2023-09-15 | 0
DA23-046 | Winfree Academy Charter Schools | 057-828 | 2023-02-10 | 2023-10-13 | 0
DA23-047 | Grapevine-Colleyville Independent School District | 220-906 | 2023-02-10 | 2023-11-10 | -2707
DA23-048 | Harmony Public Schools - West Texas | 071-806 | 2023-02-10 | 2023-10-13 | 0
DA23-049 | Rockwall Independent School District | 199-901 | 2023-02-10 | 2024-02-02 | -1496
DA23-050 | Waller Independent School District | 237-904 | 2023-02-10 | 2024-02-09 | -14014
DA23-051 | Odyssey Academy Inc. | 084-802 | 2023-02-10 | 2023-11-17 | -882
DA23-052 | Gregory-Portland Independent School District | 205-902 | 2023-02-10 | 2024-01-12 | 0
DA23-053 | Royal Independent School District | 237-905 | 2023-02-10 | 2023-12-29 | -3911
DA23-054 | Brownwood Independent School District | 025-902 | 2023-02-10 | 2023-12-08 | -1684
DA23-055 | Southwest Public Schools | 101-838 | 2023-02-10 | 2023-12-08 | -4474
DA23-056 | Zapata County Independent School District | 253-901 | 2023-02-10 | 2024-02-02 | 0
DA23-057 | Columbia-Brazoria Independent School District | 020-907 | 2023-02-10 | 2023-10-27 | -1562
DA23-058 | Life School | 057-807 | 2023-02-10 | 2024-02-02 | -107
DA23-059 | Harmony Public Schools - Houston South | 101-846 | 2023-02-10 | 2023-12-08 | -93
DA23-060 | Harmony Public Schools - Houston North | 101-858 | 2023-02-10 | 2023-10-13 | 0
DA23-061 | School of Science and Technology | 015-827 | 2023-02-10 | 2024-02-09 | -823
DA23-062 | Advantage Academy | 057-806 | 2023-02-10 | 2023-11-10 | -8239
DA23-063 | Santa Fe Independent School District | 084-909 | 2023-02-10 | 2023-11-17 | -26023
DA23-064 | Karnes City Independent School District | 128-901 | 2023-02-10 | 2023-12-08 | -2109
DA23-065 | Flatonia Independent School District | 075-901 | 2023-02-10 | 2023-10-27 | -12768
DA23-066 | Nursery Independent School District | 235-904 | 2023-02-10 | 2023-11-10 | -33705
DA23-067 | Rains Independent School District | 190-903 | 2023-02-10 | 2023-10-06 | -6980
DA23-068 | Burnham Wood Charter School District | 071-801 | 2023-02-10 | 2023-11-10 | -2316
DA23-069 | Hico Independent School District | 097-903 | 2023-02-10 | 2024-04-19 | -6492
DA23-070 | Kountze Independent School District | 100-903 | 2023-02-10 | 2023-11-10 | -817
DA23-071 | Moulton Independent School District | 143-902 | 2023-02-10 | 2024-03-15 | -16609
DA23-072 | Blackwell Consolidated Independent School District | 177-903 | 2023-02-10 | 2023-11-10 | 0
DA23-073 | Gatesville Independent School District | 050-902 | 2023-02-10 | 2023-08-11 | 0
DA23-074 | Texas School of the Arts | 220-814 | 2023-02-10 | 2024-03-15 | -5090
DA23-075 | Orange Grove Independent School District | 125-903 | 2023-02-10 | 2023-09-15 | -8482
DA23-076 | Chapel Hill Independent School District | 225-906 | 2023-02-10 | 2023-10-13 | 0
DA23-077 | Cuero Independent School District | 062-901 | 2023-08-11
DA23-078 | Academy of Accelerated Learning Inc. | 101-810 | 2023-08-11
DA23-079 | Elkhart Independent School District | 001-903 | 2023-08-11 | 2024-12-06
DA23-080 | Slocum Independent School District | 001-909 | 2023-08-11 | 2024-10-25 | 0
DA23-081 | Pleasanton Independent School District | 007-905 | 2023-08-11 | 2024-08-16 | -11322
DA23-082 | Pawnee Independent School District | 013-902 | 2023-08-11
DA23-083 | Compass Rose Public Schools | 015-838 | 2023-08-11
DA23-084 | Lackland Independent School District | 015-913 | 2023-08-11 | 2024-11-22 | 0
DA23-085 | Caldwell Independent School District | 026-901 | 2023-08-11 | 2024-08-23 | -952
DA23-086 | Dimmitt Independent School District | 035-901 | 2023-08-11
DA23-087 | Jacksonville Independent School District | 037-904 | 2023-08-11
DA23-088 | Prosper Independent School District | 043-912 | 2023-08-11
DA23-089 | Inspired Vision Academy | 057-830 | 2023-08-11 | 2024-09-20 | -2639
DA23-090 | Canutillo Independent School District | 071-907 | 2023-08-11
DA23-091 | Stephenville Independent School District | 072-903 | 2023-08-11
DA23-092 | Lamar Consolidated Independent School District | 079-901 | 2023-08-11
DA23-093 | Two Dimensions Preparatory Academy | 101-840 | 2023-08-11 | 2024-11-08 | 0
DA23-094 | Coahoma Independent School District | 114-902 | 2023-08-11 | 2024-09-20 | 0
DA23-095 | Falls City Independent School District | 128-904 | 2023-08-11 | 2024-11-08 | 0
DA23-096 | Sudan Independent School District | 140-908 | 2023-08-11 | 2024-11-22 | 0
DA23-097 | Roma Independent School District | 214-903 | 2023-08-11 | 2024-11-22 | -8628
DA23-098 | Azle Independent School District | 220-915 | 2023-08-11 | 2024-09-24 | -3991
DA23-099 | Monahans-Wickett-Pyote Independent School District | 238-902 | 2023-08-11 | 2024-11-08 | 0
DA23-100 | Thrall Independent School District | 246-912 | 2023-08-11 | 2024-11-08 | 0
DA23-101 | Alamo Heights Independent School District | 015-901 | 2023-08-11 | 2024-11-01 | -36498
DA23-102 | Red Oak Independent School District | 070-911 | 2023-08-11 | 2024-11-08 | -13129
DA23-103 | Liberty-Eylau Independent School District | 019-908 | 2023-08-11 | 2024-12-13
DA23-104 | Celina Independent School District | 043-903 | 2023-08-11
DA23-105 | Hurst-Euless-Bedford Independent School District | 220-916 | 2023-08-11
DA23-106 | East Central Independent School District | 015-911 | 2023-08-11
DA23-107 | Lumberton Independent School District | 100-907 | 2023-08-11 | 2024-11-15 | -9435
DA23-108 | Boerne Independent School District | 130-901 | 2023-08-11
DA23-109 | Cisco Independent School District | 067-902 | 2023-08-11
DA23-110 | Mount Enterprise Independent School District | 201-907 | 2023-08-11 | 2024-09-24 | -10529
DA23-111 | Joshua Independent School District | 126-905 | 2023-08-11 | 2024-12-06
DA23-112 | Montgomery Independent School District | 170-903 | 2023-08-11 | 2024-09-27 | -4313
DA23-113 | Gainesville Independent School District | 049-901 | 2023-08-11 | 2024-11-08 | -8481
DA23-114 | Jacksboro Independent School District | 119-902 | 2023-08-11 | 2024-08-16 | -94
DA23-115 | River Road Independent School District | 188-902 | 2023-08-11 | 2024-09-20 | -5633
DA23-116 | Poth Independent School District | 247-904 | 2023-08-11 | 2024-09-27 | -2928
DA23-117 | Faith Family Academy | 070-801 | 2023-08-11 | 2024-11-22 | -595
DA23-118 | Harmony Public Schools - North Texas | 161-807 | 2023-08-11
DA23-119 | Bastrop Independent School District | 011-901 | 2023-08-11
DA23-120 | Sharyland Independent School District | 108-911 | 2023-08-11 | 2024-11-22 | -206
DA23-121 | Farmersville Independent School District | 043-904 | 2023-08-11 | 2024-11-22 | -3375
DA23-122 | Copperas Cove Independent School District | 050-910 | 2023-08-11 | 2024-09-27 | -732
DA23-123 | San Elizario Independent School District | 071-904 | 2023-08-11 | 2024-11-22 | -101
DA23-124 | Vanguard Academy | 108-808 | 2023-08-11 | 2024-11-01 | -505
DA23-125 | Kerrville Independent School District | 133-903 | 2023-08-11 | 2024-12-06
DA23-126 | Ingram Independent School District | 133-904 | 2023-08-11 | 2024-12-06
DA23-127 | Paris Independent School District | 139-909 | 2023-08-11 | 2024-09-27 | -6306
DA23-128 | Slaton Independent School District | 152-903 | 2023-08-11 | 2024-09-20 | 0
DA23-129 | Bay City Independent School District | 158-901 | 2023-08-11 | 2024-11-08 | -5757
DA23-130 | McGregor Independent School District | 161-909 | 2023-08-11
DA23-131 | Rockdale Independent School District | 166-904 | 2023-08-11 | 2024-08-02 | 0

## CR23
Review Number | LEA Name | CDN | Step 1 | Step 15
CR23-001 | Elevate Collegiate Charter School | 101-877 | 2023-03-31 | 2024-09-27
CR23-002 | Prelude Preparatory Charter School | 015-843 | 2023-03-31 | 2024-08-23
CR23-003 | Royal Public Schools | 015-842 | 2023-03-31 | 2024-08-16
CR23-004 | Anderson-Shiro Consolidated Independent School District | 093-901 | 2023-03-31 | 2024-08-16
CR23-005 | Woodson Independent School District | 224-902 | 2023-03-31 | 2024-05-24
CR23-006 | Howe Independent School District | 091-905 | 2023-03-31 | 2024-05-24
CR23-007 | Carlisle Independent School District | 201-913 | 2023-03-31 | 2024-05-24
CR23-008 | La Feria Independent School District | 031-905 | 2023-03-31 | 2024-06-07
CR23-009 | Caddo Mills Independent School District | 116-901 | 2023-03-31 | 2024-05-24
CR23-010 | Leonard Independent School District | 074-909 | 2023-03-31 | 2024-08-16
CR23-011 | Grand Saline Independent School District | 234-904 | 2023-03-31 | 2024-04-05
CR23-012 | Dalhart Independent School District | 056-901 | 2023-03-31 | 2024-08-16
CR23-013 | Sabine Independent School District | 092-906 | 2023-03-31 | 2024-05-17
CR23-014 | Olney Independent School District | 252-903 | 2023-03-31 | 2024-09-20
CR23-015 | Booker Independent School District | 148-901 | 2023-03-31 | 2024-05-17
CR23-016 | Highland Park Independent School District | 188-903 | 2023-03-31 | 2024-06-21
CR23-017 | Bovina Independent School District | 185-901 | 2023-03-31 | 2024-05-17
CR23-018 | Troup Independent School District | 212-904 | 2023-03-31 | 2024-08-23
CR23-019 | S and S Consolidated Independent School District | 091-914 | 2023-03-31 | 2024-05-10
CR23-020 | Campbell Independent School District | 116-910 | 2023-03-31 | 2024-10-04
CR23-021 | Canadian Independent School District | 106-901 | 2023-03-31 | 2024-09-27
CR23-022 | May Independent School District | 025-905 | 2023-03-31 | 2024-08-16
CR23-023 | San Isidro Independent School District | 214-902 | 2023-03-31 | 2024-07-12

## F23
Review Number | LEA Name | CDN | Step 1 | Step 15
F23-001 | Mansfield Independent School District | 220-908 | 2023-03-31 | 2024-06-21
F23-002 | Pecos-Barstow-Toyah Independent School District | 195-901 | 2023-03-31 | 2024-05-24
F23-003 | Andrews Independent School District | 002-901 | 2023-03-31 | 2024-06-21
F23-004 | Universal Academy | 057-808 | 2023-03-31 | 2024-12-13
F23-005 | Texas College Preparatory Academies | 221-801 | 2023-03-31 | 2024-06-28
F23-006 | Lake Dallas Independent School District | 061-912 | 2023-03-31 | 2024-05-10
F23-007 | Southside Independent School District | 015-917 | 2023-03-31 | 2024-06-28
F23-008 | Princeton Independent School District | 043-911 | 2023-03-31 | 2024-11-08
F23-009 | Whitehouse Independent School District | 212-906 | 2023-03-31 | 2024-08-23

## CA23
Review Number | LEA Name | CDN | Step 1 | Step 11 | Adjustment Amount
CA23-001 | Alief Independent School District | 101-903 | 2023-06-23 | 2023-07-21 | 0
CA23-002 | Bryan Independent School District | 021-902 | 2023-06-23 | 2023-07-21 | 0
CA23-003 | Commerce Independent School District | 116-903 | 2023-06-23 | 2023-07-21 | 0
CA23-004 | Dickinson Independent School District | 084-901 | 2023-06-23 | 2023-08-11 | 0
CA23-005 | Dodd City Independent School District | 074-904 | 2023-06-23 | 2024-02-09 | -1598
CA23-006 | Freer Independent School District | 066-903 | 2023-06-23 | 2023-08-25 | 0
CA23-007 | Frenship Independent School District | 152-907 | 2023-06-23 | 2023-09-29 | 0
CA23-008 | Galena Park Independent School District | 101-910 | 2023-06-23 | 2023-08-11 | 0
CA23-009 | Hudson Independent School District | 003-902 | 2023-06-23 | 2023-08-25 | 0
CA23-010 | Lewisville Independent School District | 061-902 | 2023-06-23 | 2023-11-10 | 0
CA23-011 | Lockhart Independent School District | 028-902 | 2023-06-23 | 2024-04-19 | -52815
CA23-012 | Manor Independent School District | 227-907 | 2023-06-23 | 2024-04-19 | -65132
CA23-013 | Mansfield Independent School District | 220-908 | 2023-06-23 | 2023-08-11 | 0
CA23-014 | Marble Falls Independent School District | 027-904 | 2023-06-23 | 2023-11-10 | 0
CA23-015 | Midlothian Independent School District | 070-908 | 2023-06-23 | 2024-05-17 | -67573
CA23-016 | Olfen Independent School District | 200-906 | 2023-06-23 | 2024-03-15 | 0
CA23-017 | Plano Independent School District | 043-910 | 2023-06-23 | 2024-03-15 | 0
CA23-018 | Round Rock Independent School District | 246-909 | 2023-06-23 | 2023-08-11 | 0
CA23-019 | Seguin Independent School District | 094-901 | 2023-06-23 | 2024-03-15 | 0
CA23-020 | Tuloso-Midway Independent School District | 178-912 | 2023-06-23 | 2024-04-26 | -12165

## Steps-FY24
Compliance and | Step | Description | Responsibility | Electronic
Followup Reviews | Step 1 | Mail Engagement Letters | Manager | Mailed
| Step 2 | Receive Phase 1 Docs (Questionnaire) | Auditor III | N/A
| Step 3 | Request Phase 2 Docs (Student Sample) | Auditor III
| Step 4 | Receive Phase 2 Docs (Student Sample) | Auditor III
| Step 5 | Analyze Docs and Complete Workpaper Review | Auditor III
| Step 6 | Complete Prelim Report and Route for Review | Auditor III
| Step 7 | First Review Complete and Route for Second Review | Auditor IV
| Step 8 | Second Review Complete and Route for Mailing | Manager
| Step 9 | Mail Prelim Report | Auditor IV
| Step 10 | Receive Response/CAP | Auditor III
| Step 11 | Analyze Response/CAP and Update Workpapers as Needed | Auditor III
| Step 12 | Complete Final Report and Route for Review | Auditor III
| Step 13 | First Review Complete and Route for Second Review | Auditor IV
| Step 14 | Second Review Complete and Route for Mailing | Manager
| Step 15 | Mail Final Report | Auditor IV
| Step 16 | Scan Documents into Alfresco and File Audit Folder | Auditor IV
| Step 17 | Finalize and Close Electronic Working File and Move to Electronic File Cabinet | Auditor IV
Desk Audits | Step | Description | Responsibility
| Step 1 | Mail Engagement Letters | Manager
| Step 2 | Receive Documentation from LEA | Auditor III
| Step 3a | Analyze Docs and Complete Kinder Under 5 Query | Auditor III
| Step 3b | Analyze Docs and Complete EE No Sped Query | Auditor III
| Step 3c | Analyze Docs and Complete EE Speech Only Query | Auditor III
| Step 3d | Analyze Docs and Complete Bilingual/ESL Query | Auditor III
| Step 3e | Analyze Docs and Complete PRS Query | Auditor III
| Step 4 | Complete Prelim Report and Route for Review | Auditor III
| Step 5a | Return to Auditor for Corrections | Auditor IV
| Step 5b | Corrections Made, Re-Route for First Review | Auditor III
| Step 5c | First Review Complete and Route for Second Review | Auditor IV
| Step 6 | Second Review Complete and Route for Mailing | Manager
| Step 7 | Mail Prelim Report | Auditor IV
| Step 8 | Receive Response/CAP | Auditor III
| Step 9 | Analyze Response/CAP and Apply Revisions as Needed/Add CAP to Folder | Auditor III
| Step 10 | Complete Final Report and Route for Review | Auditor III
| Step 11 | First Review Complete and Route for Second Review | Auditor IV
| Step 12 | Second Review Complete and Route for Mailing | Manager
| Step 13 | Mail Final Report | Auditor IV
| Step 14 | Scan Documents into Alfresco | Auditor IV
| Step 15 | Submit Audit Adjustments to State Funding | Auditor IV
| Step 16 | Receive Actual Audit Adjustments from State Funding | Auditor IV
| Step 17 | Finalize and Close Electronic Working File and Move to Electronic File Cabinet | Auditor IV
Calendar Audits | Step | Description | Responsibility
| Step 1 | Mail Engagement Letters | Auditor IV
| Step 2 | Receive Documentation from LEA | Auditor IV
| Step 3 | Analyze LEA Response and Complete Working Folder | Auditor IV
| Step 4 | Complete Prelim Report and Route for Review | Auditor IV
| Step 5 | First Review Complete and Route for Mailing | Manager
| Step 6 | Mail Prelim Report | Auditor IV
| Step 7 | Receive Response/CAP | Auditor IV
| Step 8 | Analyze Response/CAP and Update Workpapers as Needed | Auditor IV
| Step 9 | Complete Final Report and Route for Review | Auditor IV
| Step 10 | First Review Complete and Route for Mailing | Manager
| Step 11 | Mail Final Report | Auditor IV
| Step 12 | Scan Documents into Alfresco | Auditor IV
| Step 13 | Submit Audit Adjustments to State Funding | Auditor IV
| Step 14 | Receive Actual Audit Adjustments from State Funding | Auditor IV
| Step 15 | Finalize and Close Electronic Working File and Move to Electronic File Cabinet | Auditor IV

## CR24
Review Number | LEA Name | CDN | Step 1 | Step 15
CR24-001 | Doral Academy of Texas | 105-804 | 2024-03-29
CR24-002 | Rocketship Public Schools | 220-820 | 2024-03-29
CR24-003 | Thrive Center for Success | 170-802 | 2024-03-29
CR24-004 | Essence Preparatory Charter School | 015-844 | 2024-03-29
CR24-005 | Triumph Public High Schools-Lubbock | 152-803 | 2024-03-29
CR24-006 | Texans Can Academies | 057-804 | 2024-03-29

## F24
Review Number | LEA Name | CDN | Step 1 | Step 15
F24-001 | Ingleside Independent School District | 205-903 | 2024-03-29
F24-002 | San Felipe-Del Rio Consolidated Independent School District | 233-901 | 2024-03-29
F24-003 | Hull-Daisetta Independent School District | 146-905 | 2024-03-29
F24-004 | Athens Independent School District | 107-901 | 2024-03-29
F24-005 | Crowley Independent School District | 220-912 | 2024-03-29
F24-006 | Dumas Independent School District | 171-901 | 2024-03-29
F24-007 | University of Texas University Charter School | 227-806 | 2024-03-29
F24-008 | Galveston Independent School District | 084-902 | 2024-03-29
F24-009 | Navarro Independent School District | 094-903 | 2024-03-29
F24-010 | Snyder Independent School District | 208-902 | 2024-03-29
F24-011 | YES Prep Public Schools Inc. | 101-845 | 2024-03-29
F24-012 | Alvarado Independent School District | 126-901 | 2024-03-29
F24-013 | Longview Independent School District | 092-903 | 2024-03-29
F24-014 | La Porte Independent School District | 101-916 | 2024-03-29
F24-015 | West Oso Independent School District | 178-915 | 2024-03-29
F24-016 | Clarksville Independent School District | 194-904 | 2024-03-29
F24-017 | Wylie Independent School District | 221-912 | 2024-03-29
F24-018 | Village Tech Schools | 057-847 | 2024-03-29
F24-019 | San Elizario Independent School District | 071-904 | 2024-03-29
F24-020 | Pineywoods Community Academy | 003-801 | 2024-03-29
F24-021 | Pleasanton Independent School District | 007-905 | 2024-03-29

## DA24
Audit Number | LEA Name | CDN | Step 1 | Step 13 | Adjustment Amount
DA24-001 | Houston Independent School District | 101-912 | 2024-03-15
DA24-002 | Cypress-Fairbanks Independent School District | 101-907 | 2024-03-15
DA24-003 | Pasadena Independent School District | 101-917 | 2024-03-15
DA24-004 | Sherman Independent School District | 091-906 | 2024-03-15
DA24-005 | Hallsville Independent School District | 102-904 | 2024-03-15
DA24-006 | Carrollton-Farmers Branch Independent School District | 057-903 | 2024-03-15
DA24-007 | Frisco Independent School District | 043-905 | 2024-03-15
DA24-008 | Killeen Independent School District | 014-906 | 2024-03-15
DA24-009 | Midland Independent School District | 165-901 | 2024-03-15
DA24-010 | Ysleta Independent School District | 071-905 | 2024-03-15
DA24-011 | Chapel Hill Independent School District | 212-909 | 2024-03-15
DA24-012 | Forney Independent School District | 129-902 | 2024-03-15
DA24-013 | Edgewood Independent School District | 015-905 | 2024-03-15
DA24-014 | Hamshire-Fannett Independent School District | 123-914 | 2024-03-15
DA24-015 | Hereford Independent School District | 059-901 | 2024-03-15
DA24-016 | George I. Sanchez Charter | 101-804 | 2024-03-15
DA24-017 | Eanes Independent School District | 227-909 | 2024-03-15
DA24-018 | Wichita Falls Independent School District | 243-905 | 2024-03-15
DA24-019 | Mathis Independent School District | 205-904 | 2024-03-15
DA24-020 | Cedar Hill Independent School District | 057-904 | 2024-03-15
DA24-021 | Rusk Independent School District | 037-907 | 2024-03-15 | 2024-12-13

## CA24
Review Number | LEA Name | CDN | Step 1 | Step 11 | Adjustment Amount
CA24-001 | Brazosport Independent School District | 020-905 | 2024-06-14 | 2024-09-20 | 0
CA24-002 | Lockhart Independent School District | 028-902 | 2024-06-14 | 2024-12-13
CA24-003 | Gainesville Independent School District | 049-901 | 2024-06-14 | 2024-11-22 | 0
CA24-004 | Friendswood Independent School District | 084-911 | 2024-06-14 | 2024-08-16 | 0
CA24-005 | Collinsville Independent School District | 091-902 | 2024-06-14 | 2024-09-06 | -12434
CA24-006 | Howe Independent School District | 091-905 | 2024-06-14
CA24-007 | Whitewright Independent School District | 091-910 | 2024-06-14
CA24-008 | S and S Consolidated Independent School District | 091-914 | 2024-06-14
CA24-009 | Commerce Independent School District | 116-903 | 2024-06-14
CA24-010 | Mullin Independent School District | 167-902 | 2024-06-14 | 2024-08-16 | 0
CA24-011 | Conroe Independent School District | 170-902 | 2024-06-14
CA24-012 | Manor Independent School District | 227-907 | 2024-06-14
CA24-013 | Granger Independent School District | 246-905 | 2024-06-14